## Sheet2
Tasks | 2018-10-01 |  |  |  | 2018-11-01 |  |  |  | 2018-12-01 |  |  |  | 2019-01-01 |  |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  | 2019-04-01
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
2.0 - Project
2.1 - Artefact
2.1.1 - Research FPS games in today's market
2.1.2 - Research the evolution of FPS games
2.1.3 - Design the FPS Game
2.1.4 - Create desired models
2.1.5 - Develop first FPS game (controls non-simplified)
2.1.6 - Research the history of simplifying controls within games
2.1.7 - Investigate, develop and explore different FPS controls
2.1.8 - Clone the existing FPS game and implement findings (simplifying controls)
2.1.9 - Testing
2.2 - Documentation
2.2.1 - Carry out additional risk assessment before testing
2.2.2 - Review and organise all previous research
2.2.3 - Organise and analyse test data
2.2.4 - Document test results
2.2.5 - Draw conclusion
Information
Out of Office
Away from task
Working on larger task
Working on smaller task
Complete
Optional Work
FPS: First-Person Shooters

## icons
10003
#VALUE!
12147

## Sheet1 (hidden)
Document subject to change throughout design stage. | Consider designing application for location owners to use to add items.
|  | 1. Induction programs. |  | time limit :: leaderboarDS_ :: induces competitiive nature
2. Professional skills enhancement.
|  | 4. Soft skills enhancement. |  | avatars :: rewarDS_ :: personal approach :: emotional induction
5. Behavioral change.
6. Gamify assessments for traditional eLearning courses (partial gamification).
https://elearningindustry.com/6-killer-examples-gamification-in-elearning