## Sheet2
Tasks | 2018-10-01 |  |  |  | 2018-11-01 |  |  |  | 2018-12-01 |  |  |  | 2019-01-01 |  |  |  | 2019-02-01 |  |  |  | 2019-03-01 |  |  |  | 2019-04-01
| W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1.0 - Proposal
1.1 - Research Literature and highlight Areas of Interest | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
1.2 - Draft Introduction | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
1.3 - Draft Aims and Objectives | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
1.4 - Draft Academic Literature Review | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
1.5 - Gantt Chart Completion | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
1.6 - Risk Management Reviewed | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
1.7 - Review Proposal | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
2.0 - Project | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
2.1 - Artefact | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
2.1.1 - Research FPS games in today's market | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
2.1.2 - Research the evolution of FPS games | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
2.1.3 - Design the FPS Game | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
2.1.4 - Create desired models | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
2.1.5 - Develop first FPS game (controls non-simplified) | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
2.1.6 - Research the history of simplifying controls within games | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
2.1.7 - Investigate, develop and explore different FPS controls | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
2.1.8 - Clone the existing FPS game and implement findings (simplifying controls) | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
2.1.9 - Testing | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
2.2 - Documentation | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
2.2.1 - Carry out additional risk assessment before testing | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
2.2.2 - Review and organise all previous research | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
2.2.3 - Organise and analyse test data | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
2.2.4 - Document test results | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
2.2.5 - Draw conclusion | bar: 2018-10-01 W1 to 2018-12-01 W3; 2019-01-01 W3 to 2019-04-01 W4
Information
Out of Office
Away from task
Working on larger task
Working on smaller task
Complete
Optional Work
FPS: First-Person Shooters

## icons
10003
#VALUE!
12147

## Sheet1 (hidden)
Document subject to change throughout design stage. | Consider designing application for location owners to use to add items.
|  | 1. Induction programs. |  | time limit :: leaderboarDS_ :: induces competitiive nature
2. Professional skills enhancement.
|  | 4. Soft skills enhancement. |  | avatars :: rewarDS_ :: personal approach :: emotional induction
5. Behavioral change.
6. Gamify assessments for traditional eLearning courses (partial gamification).
https://elearningindustry.com/6-killer-examples-gamification-in-elearning