## Sheet1
General Hazard & Risk Assessment
| Assessed by: Christopher Ross |  |  |  | Date of Assessment: 08/10/2018
Time-Loss Classification [s] |  |  | Likelihood of Occurance [p] |  |  | Criticality Number [c/no]
1 - Negligible 2- Minor 3 - Major 4 - Hazardous 5 - Catastrophic |  |  | 1 - Extremely Unlikely 2 - Very Unlikely 3 - Unlikely 4 - Likely 5 - Very Likely |  |  | L - Low 1 - 7 M - Medium 8 - 16 H - High 17- 25
Potential Risk |  | Result of Occurance |  | Mitigation |  |  | S | P | C/No | Risk Level
Lack of test participants |  | Inaccurate data readings |  | Perform user tests with questionaires where ever and when ever possible, inside and outside of university. |  |  | 3 | 2 | 6 | L
Strain/headaches caused by gaming or looking at a screen for an excessive amount of time |  | Possible incompletetion of test due to the participant leaving before finishing |  | Allowing a five to ten minute break when switching games |  |  | 2 | 4 | 8 | M
Themes presented in the artefact such as violence and death may cause discomfort to testers |  | Distress to users |  | Ensure the user knows what they will be testing before proceeding and replace enemies with human silhouette targets. |  |  | 2 | 4 | 8 | M
Not retaining the same participants for the duration of the project |  | This will skew the data, participant must complete both game tests. |  | Allow testing to be ran on different days. So that if one participant is not able to turn up, they may turn up on another day. |  |  | 4 | 2 | 8 | M
Unreliable Game Engine insufficient Resources/Material |  | Game development would not able to continue |  | Research and choose a game engine that has sufficient recourses |  |  | 3 | 4 | 12 | M
Disinterested test participants / making a mockery of test questionaire |  | Skewed/Inaccurate data readings |  | Before taking the questionaire, I should allow myself a time to ensure that the user is interested in the partaking of the test |  |  | 3 | 5 | 15 | M
Delays or set backs in designing/developing either version of the game |  | Loss of time |  | Use every resource available on the game engine website, youtube or google |  |  | 4 | 5 | 20 | H
Game may lag due to graphics being to demanding on the system |  | User discomfort / unable to complete test |  | Create a settings menu that allows me or the user to set the graphics to either low, medium or high. |  |  | 4 | 5 | 20 | H